# Baby Monitor Development Timeline

Complete Prototyping & Development Guide

# Executive Summary

Project Goal: Develop a premium baby monitoring system with two product tiers (Core at $99, Pro at $299) featuring video monitoring, environmental sensing, AI detection, and cloud connectivity.

Timeline: 12 weeks for prototype development, followed by 8-12 weeks for production design and manufacturing setup.

Initial Investment: $250-330 for prototyping hardware, $90,000 for software development, $35,000-70,000 for production tooling (NRE).

# Product Specifications

## Core Model - $99

- • Video: 720p camera

- • Storage: 32GB eMMC (24 hours of recording)

- • Sensors: Temperature and humidity only

- • Processing: ESP32-S3 or similar (cloud-dependent for AI)

- • Audio: Mono speaker

- • Battery: 500-1000mAh (shutdown protection only)

- • Connectivity: WiFi + Bluetooth

- • Power: USB-C charging with magnetic battery connector

- • Manufacturing Cost: $32-40

## Pro Model - $299

- • Video: 4K camera with enhanced low-light performance

- • Storage: 512GB eMMC (72 hours of 4K recording)

- • Sensors: Full suite (temp, humidity, air quality, light, vibration)

- • Processing: RK3588 or NXP i.MX 8M Plus with NPU (on-device AI)

- • Audio: Premium stereo/high-quality speaker

- • Battery: 7000mAh internal (8-10 hours operation)

- • Connectivity: Dual-band WiFi + Bluetooth + Thread (Matter-ready)

- • Power: USB-C charging with magnetic battery connector

- • Manufacturing Cost: $165-185

## Extended Battery Pack (Accessory) - $79

- • Capacity: 12,000mAh magnetic attachment

- • Runtime: 24+ hours for Core, 34+ hours total for Pro

- • Compatible with both Core and Pro models

- • Manufacturing Cost: $28-35

# Subscription Model

Note: All subscriptions are account-based (not per-device). One subscription covers all devices on the account.

## Free Tier (Included with Device)

- • Local network streaming (unlimited)

- • On-device storage (24-72 hours based on model)

- • On-device AI detection (Pro model only)

- • Push notifications (unlimited)

- • Remote viewing (10 hours/month)

- • Two-way audio

- • Environmental monitoring

## Cloud Storage Plan - $9.99/month ($99.99/year)

- • 30-day cloud video storage

- • Unlimited remote viewing

- • 100GB saved recordings library

- • Multi-device viewing/sharing

- • Download/export capabilities

Cloud Cost: $5-7/month per account

## AI Insights Plan - $9.99/month ($99.99/year)

- • Advanced pattern analysis

- • Sleep quality scoring

- • Developmental milestone tracking

- • Breathing monitoring via AI

- • Unusual event detection

- • Weekly reports and insights

Cloud Cost: $5-8/month per account

## Complete Plan - $17.99/month ($179.99/year)

- • All Cloud Storage features

- • All AI Insights features

- • Priority support

- • Early access to new features

Cloud Cost: $13-15/month per account

# Phase 1: Prototyping Hardware Setup

Timeline: Week 0 (Immediate)

Budget: $250-330

## Required Components

Core Components:

- ☐ Raspberry Pi 4 (4GB) - $55

- ☐ Raspberry Pi Camera Module 3 - $25

- ☐ Official Pi USB-C Power Supply (5V/3A) - $10

- ☐ 128GB microSD Card (A2 rated, UHS-I) - $15

Environmental Sensors:

- ☐ BME680 Breakout Board (temp/humidity/pressure/air quality) - $20

- ☐ BH1750 Light Sensor - $8

- ☐ ADXL345 Accelerometer (motion/vibration) - $10

Audio Components:

- ☐ USB Audio Adapter with Microphone - $15

- ☐ Small Speaker (3-5W) - $10

Wiring & Prototyping:

- ☐ Half-size Breadboard - $5

- ☐ Male-Female Jumper Wires (40-piece set) - $5

- ☐ GPIO Extension/T-Cobbler (optional) - $5

Optional:

- ☐ Raspberry Pi Case - $12

## Recommended Retailers

- • Adafruit.com - Excellent tutorials and documentation

- • SparkFun.com - Good documentation and support

- • Amazon - Faster shipping, verify sellers

- • Official Raspberry Pi retailers - Check raspberrypi.com

# Phase 2: Initial Setup & Basic Functionality

Timeline: Weeks 1-2

## Week 1: System Setup

Tasks:

- ☐ Install Raspberry Pi OS (64-bit, latest version)

- ☐ Configure WiFi and SSH access

- ☐ Update system packages (apt update && apt upgrade)

- ☐ Install Python development tools

- ☐ Set up Git repository for version control

Camera Setup:

- ☐ Connect Camera Module 3 to CSI port

- ☐ Enable camera in raspi-config

- ☐ Test camera with 'libcamera-hello' command

- ☐ Capture test images and video

- ☐ Install picamera2 library

- ☐ Write basic Python script for video capture

Deliverables:

- • Working Raspberry Pi with camera capturing 1080p video

- • Development environment set up

- • Basic Python scripts for camera control

## Week 2: Sensor Integration

Tasks:

- ☐ Enable I2C interface in raspi-config

- ☐ Connect BME680 sensor to I2C pins (GPIO 2/3)

- ☐ Install Adafruit CircuitPython libraries

- ☐ Test BME680 sensor readings (temp, humidity, pressure, gas)

- ☐ Connect and test BH1750 light sensor

- ☐ Connect and test ADXL345 accelerometer

- ☐ Create sensor logging script (log to CSV every 30 seconds)

- ☐ Verify all sensors working simultaneously

Deliverables:

- • All environmental sensors connected and reading data

- • Data logging system operational

- • Basic visualization of sensor data

# Phase 3: Streaming & Storage

Timeline: Weeks 3-4

## Week 3: Video Streaming

Tasks:

- ☐ Install FFmpeg for video encoding

- ☐ Set up RTSP streaming server (using rpicam-vid or custom)

- ☐ Test RTSP stream from VLC on computer

- ☐ Implement mDNS/Bonjour for device discovery

- ☐ Create simple web interface using Flask

- ☐ Embed video player in web interface

- ☐ Test streaming from phone browser (same WiFi network)

- ☐ Optimize streaming bitrate and latency

Deliverables:

- • Working local network video streaming

- • Basic web interface for viewing stream

- • Device discoverable on local network

## Week 4: Local Storage & Playback

Tasks:

- ☐ Implement continuous video recording to SD card

- ☐ Create file rotation system (keep last 24 hours)

- ☐ Implement storage space monitoring

- ☐ Add video playback to web interface

- ☐ Create timeline scrubber for recorded video

- ☐ Add thumbnail generation for quick preview

- ☐ Test simultaneous recording and streaming

- ☐ Measure storage usage and calculate capacity

Deliverables:

- • Continuous recording with automatic rotation

- • Playback interface for recorded footage

- • Storage management system

# Phase 4: Audio & Detection

Timeline: Weeks 5-6

## Week 5: Two-Way Audio

Tasks:

- ☐ Configure USB audio adapter

- ☐ Test microphone input (record and play back)

- ☐ Test speaker output (play test sounds)

- ☐ Install PyAudio library

- ☐ Implement audio streaming from device to app

- ☐ Implement audio streaming from app to device (talk-back)

- ☐ Add audio playback controls to web interface

- ☐ Test audio quality and latency

- ☐ Implement basic lullaby/white noise playback

Deliverables:

- • Two-way audio communication working

- • Lullaby/white noise features

- • Audio controls in web interface

## Week 6: Basic Detection

Tasks:

- ☐ Install OpenCV for computer vision

- ☐ Implement motion detection (frame differencing)

- ☐ Add motion detection zones/sensitivity settings

- ☐ Implement sound level detection (dB threshold)

- ☐ Create alert system for motion/sound events

- ☐ Log all detection events with timestamps

- ☐ Add event markers to video timeline

- ☐ Test false positive/negative rates

Deliverables:

- • Working motion detection

- • Sound level monitoring and alerts

- • Event logging system

# Phase 5: System Integration

Timeline: Weeks 7-8

## Week 7: Unified Application

Tasks:

- ☐ Combine all components into single application

- ☐ Create modular architecture (video, audio, sensors, storage modules)

- ☐ Implement configuration file system

- ☐ Add logging system for debugging

- ☐ Create systemd service for auto-start on boot

- ☐ Test reliability (24+ hour continuous operation)

- ☐ Implement graceful shutdown procedures

- ☐ Add error handling and recovery mechanisms

Deliverables:

- • Integrated application running all features

- • Auto-start on boot capability

- • Stable 24+ hour operation

## Week 8: Mobile Interface

Tasks:

- ☐ Design mobile-responsive web interface

- ☐ Implement dashboard showing live feed and sensor data

- ☐ Add controls for audio playback and two-way talk

- ☐ Create settings page (detection sensitivity, alert preferences)

- ☐ Add event history/timeline view

- ☐ Implement data visualization for environmental sensors

- ☐ Test on multiple devices (iOS, Android)

- ☐ Optimize for touch controls and mobile bandwidth

Deliverables:

- • Polished mobile web interface

- • Full control from smartphone

- • Data visualization and history

# Phase 6: AI Features (Optional but Recommended)

Timeline: Weeks 9-10

Additional Cost: $60 for Google Coral USB Accelerator

## Week 9: Coral Setup & Person Detection

Tasks:

- ☐ Order Google Coral USB Accelerator

- ☐ Install Edge TPU runtime and PyCoral library

- ☐ Download pre-trained models from Coral model zoo

- ☐ Test person detection model on camera feed

- ☐ Measure inference speed and accuracy

- ☐ Implement baby presence detection

- ☐ Add alerts when baby enters/exits frame

- ☐ Test in various lighting conditions

Deliverables:

- • Working person detection using Edge TPU

- • Real-time inference (<50ms)

- • Baby presence/absence alerts

## Week 10: Advanced AI Features

Tasks:

- ☐ Implement pose estimation for sleep position monitoring

- ☐ Create cry detection using audio classification

- ☐ Test different cry types (hungry, tired, discomfort)

- ☐ Implement basic activity tracking (awake/asleep)

- ☐ Add pattern logging for future analysis

- ☐ Create AI event alerts separate from motion alerts

- ☐ Test false positive rates

- ☐ Optimize for power consumption

Deliverables:

- • Pose estimation and sleep position monitoring

- • Cry detection and classification

- • Activity pattern logging

# Phase 7: Cloud Integration

Timeline: Weeks 11-12

## Week 11: Backend & Authentication

Tasks:

- ☐ Set up cloud infrastructure (AWS/GCP/Azure)

- ☐ Create backend API (Node.js/Python FastAPI)

- ☐ Implement user authentication (Firebase Auth or Auth0)

- ☐ Create user registration and login flows

- ☐ Implement device pairing/registration system

- ☐ Set up database for user accounts and device data

- ☐ Implement secure device-to-cloud communication

- ☐ Test authentication from mobile app

Deliverables:

- • Cloud backend infrastructure

- • User authentication system

- • Device pairing capability

## Week 12: Cloud Storage & Remote Access

Tasks:

- ☐ Set up cloud storage (S3/Google Cloud Storage)

- ☐ Implement video upload for motion events

- ☐ Create smart upload logic (keyframes + events only)

- ☐ Set up WebRTC TURN server for remote viewing

- ☐ Implement remote streaming (not on local network)

- ☐ Test remote access from cellular connection

- ☐ Implement push notifications (Firebase Cloud Messaging)

- ☐ Create cloud-based event history

- ☐ Test subscription feature flags (enable/disable based on tier)

Deliverables:

- • Cloud video storage working

- • Remote access from anywhere

- • Push notifications system

- • Subscription tier management

# Phase 8: Production Planning

Timeline: Weeks 13-16 (concurrent with prototype refinement)

## Processor Selection

Tasks:

- ☐ Research production-grade SoC options

- ☐ Order development boards for candidates:

  - Core Model: ESP32-S3 dev board (~$20)

  - Pro Model: RK3588 or i.MX 8M Plus dev board (~$150-200)

- ☐ Port prototype software to production processor

- ☐ Test all features on new hardware

- ☐ Measure power consumption

- ☐ Test heat generation and thermal management needs

- ☐ Validate video quality (720p for Core, 4K for Pro)

- ☐ Test AI performance (Pro model)

Deliverables:

- • Finalized processor selection for both models

- • Software ported and tested on production hardware

- • Power and thermal specifications documented

## PCB Design Planning

Tasks:

- ☐ Create detailed component list (BOM)

- ☐ Define PCB specifications:

  - Form factor and size constraints

  - Number of layers (likely 4-6)

  - Power requirements and regulation

  - Camera interface (MIPI CSI)

  - Sensor connections (I2C)

  - Audio codec and amplifier

- ☐ Research PCB design firms or freelancers

- ☐ Get quotes for PCB design ($5,000-15,000)

- ☐ Get quotes for prototype assembly (10-25 units)

- ☐ Create mechanical/industrial design specifications

Deliverables:

- • Complete BOM with part numbers and costs

- • PCB specification document

- • Vendor quotes for design and manufacturing

# Key Development Tools & Libraries

## Operating System & Core

- • Raspberry Pi OS (64-bit, latest version)

- • Python 3.9+ (primary development language)

- • Git for version control

## Video & Camera

- • picamera2 - Python library for Camera Module 3

- • libcamera - Low-level camera interface

- • opencv-python - Computer vision and video processing

- • ffmpeg - Video encoding and streaming

## Sensors

- • smbus2 or board + busio - I2C communication

- • adafruit-circuitpython-bme680 - BME680 temperature/humidity/air quality

- • adafruit-circuitpython-adxl34x - ADXL345 accelerometer

- • Adafruit_CircuitPython_BH1750 - Light sensor

## Audio

- • pyaudio - Audio I/O

- • pydub - Audio processing

- • pygame - Simple audio playback

## Web & Networking

- • flask or fastapi - Web server for local API

- • python-socketio - Real-time communication

- • requests - HTTP client

- • paho-mqtt - MQTT for IoT communication (optional)

## AI & Machine Learning

- • tflite-runtime - TensorFlow Lite (lightweight inference)

- • pycoral - Google Coral Edge TPU library

- • Pre-trained models from Coral Model Zoo

## Cloud Services

- • Firebase (Authentication, Cloud Messaging, Firestore)

- • AWS SDK (boto3) or Google Cloud SDK

- • WebRTC libraries for peer-to-peer streaming

# Testing & Validation Checklist

## Core Functionality Tests

- ☐ Video quality acceptable in daylight conditions

- ☐ Video quality acceptable in low-light conditions

- ☐ Stream latency under 500ms on local network

- ☐ Audio clarity sufficient for baby monitoring

- ☐ Two-way audio delay acceptable (under 1 second)

- ☐ All sensors reading accurate data

- ☐ Motion detection sensitivity appropriate (low false positives)

- ☐ Sound detection working reliably

- ☐ Storage rotation working (maintains 24-72 hours)

- ☐ System stable for 48+ hours continuous operation

## Connectivity Tests

- ☐ Device discoverable on local network

- ☐ Automatic reconnection after WiFi dropout

- ☐ Remote access working from cellular network

- ☐ Push notifications received promptly

- ☐ Multiple devices can view simultaneously

- ☐ Bandwidth usage reasonable for mobile data

## AI Performance Tests (if implemented)

- ☐ Person detection working accurately

- ☐ Inference time acceptable (under 100ms)

- ☐ Cry detection accuracy validated

- ☐ False positive rate acceptable (under 5%)

- ☐ AI features don't significantly impact battery life

## User Experience Tests

- ☐ Mobile interface intuitive and responsive

- ☐ Initial setup process clear and simple

- ☐ Video playback scrubbing smooth

- ☐ Settings easy to find and adjust

- ☐ Error messages helpful and actionable

- ☐ Works well on both iOS and Android

# Budget Summary

## Prototype Development (Immediate)

- • Phase 1 Hardware: $250-330

- • Phase 2 AI Hardware (optional): $60-80

- • Cloud Services (12 weeks): $120-600

Total Prototype Phase: $430-1,010

## Production Development

- • Production processor dev boards: $170-220

- • PCB Design (per model): $5,000-15,000

- • Two PCB designs (Core + Pro): $10,000-30,000

- • Prototype PCB assembly (25 units): $2,000-5,000

- • Injection mold tooling (housing): $15,000-30,000

- • Certifications (FCC, safety): $10,000-20,000

Total Production Setup (NRE): $37,000-85,000

## Software Development

- • Backend development: $30,000

- • Mobile apps (iOS + Android): $40,000

- • AI model development: $20,000

Total Software (one-time): $90,000

## First Production Run (1000 units)

- • 700 Core units @ $40: $28,000

- • 300 Pro units @ $175: $52,500

- • Packaging & accessories: $5,000

Total First Production: $85,500

GRAND TOTAL TO MARKET: $212,500-261,510

Expected Year 1 Revenue (1000 units sold): $249,270

Expected Year 1 Net Profit: $35,895

Expected Year 2+ Annual Profit: $125,895

# Immediate Next Steps

## This Week:

- 1. Order prototyping hardware (use shopping list from Phase 1)

- 2. Set up development environment while waiting for hardware

- 3. Create GitHub repository for project

- 4. Research and select cloud platform (AWS/GCP/Azure)

- 5. Begin sketching industrial design concepts

## First Month:

- 1. Complete Phases 1-2 (setup and basic functionality)

- 2. Identify and contact potential PCB design firms

- 3. Begin user testing with prototype (friends/family with babies)

- 4. Document feature requests and pain points

- 5. Set up cloud infrastructure basics

## First Quarter:

- 1. Complete all prototype phases (1-7)

- 2. Validate market interest (pre-orders, crowdfunding campaign?)

- 3. Order production processor dev boards

- 4. Begin PCB design process

- 5. Finalize product specifications and pricing

# Resources & Support

## Online Communities

- • Raspberry Pi Forums: forums.raspberrypi.com

- • Reddit: r/raspberry_pi, r/homeautomation, r/IOT

- • Adafruit Learning System: learn.adafruit.com

- • SparkFun Tutorials: learn.sparkfun.com

- • Stack Overflow: For technical questions

## Documentation

- • Raspberry Pi Official Documentation: raspberrypi.com/documentation

- • Camera Module 3 Documentation: raspberrypi.com/products/camera-module-3

- • Google Coral Documentation: coral.ai/docs

- • OpenCV Tutorials: docs.opencv.org/master/d9/df8/tutorial_root.html

- • Flask Documentation: flask.palletsprojects.com

## Manufacturing Resources

- • PCB Design: Upwork, Fiverr (freelancers), or firms like Bresslergroup

- • PCB Manufacturing: JLCPCB, PCBWay, OSH Park (prototypes)

- • Assembly: MacroFab, Tempo Automation, or contract manufacturers

- • Injection Molding: Proto Labs, Xometry (quotes)

- • Full Manufacturing: Consider Alibaba manufacturers for production runs

---

This document is a living guide. Update it as you progress through development and learn more about your product requirements and market needs.

Good luck with your baby monitor development!